## Review form
REPORTING FORM REGARDING THE IMPLEMENTATION OF ACTIVITIES ENVISAGED IN THE “ACTION PLAN ON NON-COMMUNICABLE DISEASES, 2016-2020”
STRATEGIC OBJECTIVES | SPECIFIC OBJECTIVES | ACTIVITIES | INDICATORS | ACHIEVED | COMMENTS | COST
Domain 1: Governance. STRATEGIC OBJECTIVE 1: Strengthening and expanding cross-sector cooperation and partnership for NCD | Specific objective 1.1: Strengthen the role of the intersectorial committee on NCDs by assigning it the specific responsibility of overseeing the development, implementation and evaluation of the plan to ensure engagement, policy, coherence, joint accountability and clear reporting lines. | Establish the intersectorial committee (members, terms of reference, annual working plan and regular meetings | Term of reference are completed Annual plan of work is finished. | Partially achieved | Order of Minister of Health, date 07.08.2015, No. 163, on "Setting up a national committee for the prevention and control of chronic diseases". The intersectorial committee was established but there were no regular meetings. | 2.400.000
| Specific objective 1.2: Promote integration of NCDs into relevant national development policies, e.g. health sector strategy, national integration and development strategy | Make a policy analysis of other ministries strategies in order to identify NCDs relevant activity | NCDs are prioritized in relevant national development policies | Partially achieved | NCDs are priritized and included in the National Integration and Development Strategy 2015-2020 and at the National Health Strategy 2016-2020. Also, more specifically, reproductive health cancers are prioritized in the National Strategy on Sexual and Reproductive Health 2017-2021. There is need for strengthening the inter-sectorial collaboration towards prevention and control of NCDs. | No added cost
|  | Develop recommendation and propose them to Intersectorial Committee (IC) to integrate these activity into NCD program | Recommendation are developed and proposed | Fully achieved | Recommendation are developed and proposed to IC. NCDs are a priority of the Governmet (Government Program 2017-2021). | No added cost
|  | Foster and promote Partnership public private (PPP) on promoting healthy lifestyle initiative (labor regulation) | PPP-s on health lifestyle are fostered and promoted | Fully achieved | PPP-s on health lifestyle are fostered and promoted and the best example is the Basic Medical Check-Up which aims screening and education on healthy lifestyle of individuals aged 35-70 years old. | No added cost
| Specific objective 1.3: Engage all relevant stakeholders at all levels including LG | Establish an intersectorial committee | Relevant favourable policies on NCDs are adopted | Fully achieved | The intersectorial committee was established in 2015 through the Order of the Minister of Health No. 163 Date 07/04/2015. | No added cost
|  | Identify the focal point at the stakeholders level | Focal point is identified | Fully achieved | The national focal point is located at the Institute of Public Health. Also, with regard to NCDs there are focal points located at the Regional Health Care Services Operators and at the Local Health Care Units in all the districts of Albania. Local government is not engaged in this process. | No added cost
|  | Organize a collaboration workshop on engagement for NCDs at all levels | Workshop recommendation are implemented | Partially achieved | With regard to Cancer, Coronary Artery Diseases, Cerebrovascular Accidents and Diabetes national registries workshops were organized and recommendations were implemented. | 2.200.000
| Specific objective 1.4: Include NCDs in the next iteration of the UNDAF | Include in Country Program Document (CPD) 2017-2021 | NCDs are included in the UNDAF | Fully achieved | NCDs are included in WHO program and UNFPA country programme document for Albania 2017-2021, | No added cost
| Specific objective 1.5: Review and update legislation in support of NCDs as appropriate (e.g. PH, heath system) development of new legal documents to enable interventions in NCDs. | Review and analyze the analysis legislation on NCDs (web research) | NCD related legislation is reviewed, updated and developed to enable interventions in NCDs | Fully achieved | NCD related legislation is reviewed, updated and developed to enable interventions in NCDs. There are Decisions of Council of Ministers (DCM) on: primary health care package (2019), list of reimbursable drugs (2019), financing of hospital health services from the CHCIF (2019), data collection and reporting on NCDs registries (2014). Law on Health Care was updated in 2019 and is under revision the Reproductive Health Law (which includes reproducteve health cancers). | No added cost
| Specific objective 1.6: Develop the accountability framework with clear targets, indicators, roles and responsibilities | Organize cross-sector workshop to develop clear targets, indicators, roles and responsibilities. Recommendations should be sent to the IC for approval | Targets and responsibilities are identified | Fully achieved | Plan of monitoring NCDs and progress in their control in Albania (framework indicators and their metadata) was developed in 2017. | 2.500.000
| Specific objective 1.7: To ensure its feasibility the plan needs to be incorporated within the mid-term programs of the government budget review | Annual cross-sector workshop on the presentation of the analysis of available resources (finance, human and information) on each sector | The feasibility report is presented. | Fully achieved | Annual cross-sector workshop on the presentation of the analysis of available resources (finance, human and information) on cancers and check-up program were carried out for all levels of health sector (primary health care, hospital health care and public health). This is an information required periodically by the office of Prime Minister. | Cost is included in the activity (Specific objective 1.6)
|  | Develop steps to implement the NCD program | Steps are identified, developed and implemented | Fully achieved | Analysis of available resources (finance, human and information) on cancers and check-up program were carried out for all levels of health sector (primary health care, hospital health care and public health). Based on this analysis, steps to implement specific programs were developed.
| Specific objective 1.8: Develop a communication plan for the effective engagement of the relevant stakeholders and the public | Develop community-focused NCD- related documents (prepared by health specialist). Draft a communication plan document with the focus on the stakeholders/actors | Increased involvement of relevant stakeholders and the public in NCD prevention and control activities | Partially achieved | Check-up program provides guidelines for family physicians for closely working with community but they only invite individuals aged 35-70 years to participate in screening programs (cervical cancer, breast cancer, check-up program). There are gaps in developing NCD prevention (for example healthy nutrition and physical activity etc.) and control activities. | 100.000
| Specific objective 1.9: Expand capacity of each ministry on the area of NCDs | N/A | Increased number of human resource dedicated to NCDs | Partially achieved | Ministry of Health and Social Welfare, Institute of Public Health and Ministry of Education updated the school curricula with regard to improve physical activity among schoold aged children. But the number of human resources in each Ministry dedicated to NCDs was not increased. | No added cost
Domain 2: Prevention. STRATEGIC OBJECTIVE 2: Scaling up equity-sensitive population interventions to address risk factors and its underlying social determinants | Tobacco use. Specific objective 2.1: Strengthen the implementation of FCTC with special emphasis on: closed public places tobacco advertising tax and price policy sale to minors pictorial warning labels | Strengthen the Health Inspectorate infrastructure | Health inspectorate workforce is increased and trained | Fully achieved | The State Health Inspectorate was created since 2013. The State Health Inspectorate is organized at the central level and in the 12 regions of the country with its regional branches.The inspection is carried out through the e-inspection portal and its operation throughout the territory began at the end of 2017. Regarding the increase of excise tax on alcohol products, since 2018 there have been no changes in the last 3 years. | 22.000.000
|  | Strengthen the human resource capacity - increase the number of inspectors - increase the staff capacity in monitoring the administrative acts. | Electronic platform is in place | Fully achieved | Human resources capacities are strengthened. Health inspectorate workforce is increased and trained. Since 2013, the number of health inspectors has increased and now there are about 245 inspectors across the country.
|  | Establish and maintain the electronic health inspectorate platform. | Electronic platform is in place | Fully achieved | Electronic platform (e-inspection) is in place and it is nation wide since the end of 2017. | 1.000.000
|  | Make an economic and health impact assessment of increased excise tax. | Report on the economic and health impact assessment of the increased excise tax. | Partially achieved | Law "On excises in the Republic of Albania" No. 61, date 2012 was changed in 2018 and envisaged increase of excise tax on tobacco products. But there is no report on the economic and health impact assessment of the increased excise tax. | 100.000
|  | Administrative acts on excise tax increase on tobacco product. | Excise tax is increased with a consequent increase in the retail price of tobacco products. | Fully achieved | Law "On excises in the Republic of Albania" No. 61, date 2012 was changed in 2018 and envisaged increase of excise tax on tobacco products. Regarding the increase of excise tax on tobacco products since 2018 there have been no changes in the last 3 years.
|  | Have a meeting of NCPHTP to approve the change of pictorial warning labels size in line with the EU standards | Size of pictorial warning labels are in line EU standards | Fully achieved | Size of pictorial warning labels are in line EU standards and were approved in 2020. | 100.000
| Tobacco use. Specific objective 2.2: Provide smoking cessation services through the national program of check-up and increase the affordability of Nicotine replacement Treatment (NRT) | Advocacy for including NRT in the drug reimbursement list | NRT is included in the drug reimbursement list | Not achieved | NRT is not included in the drug reimbursement list. But technical meetings for the removal of electronic cigarettes were carried out. Law "On protection of health from tobacco products" No. 9636 date 6.11.2006 was changed and updated into Law No. 56/2019 and consuming electronic cigarettes is considered smoking tobacco. | No added cost
|  | Draft the protocols/guidelines on smoking cessation. | Protocols/guideline on smoking cessation are prepared | Fully achieved | Protocols/guideline on smoking cessation were prepared and established in the framework of basic check-up program for individuals aged 35-70 years. The check-up manual “Healthy we all are equal!” is available in all health prinamry health centres. | 50000
|  | Train the health providers at the primary health care service on the smoking cessation counseling | Number of training activities on smoking cessation. Health staff at PHC are trained. | Fully achieved | In the framework of basic health check-up implementation, health staff at PHC were trained with regard to smoking cessation counseling. The check-up manual “Healthy we all are equal!” is available in all health prinamry health centres. In 2018, four trainings were carried out in 2 districts of Albania (Korce and Elbasan) with regard to "Informing and awareness raising of health personnel for importance and usefulness of basic medical check-up among people 35-70 years". During 2016-2020, with regard to smoking cessation, 17 trainings in primary health care centers of 5 districts were carried out. During the implementation of the check-up program, 270 training were carried out in 12 regions of the country. | 10.000.000
|  | Establish the outpatients reference Center on smoking cessation at UHC “Mother Teresa” | Outpatient service on smoking cessation is established | Not achieved | Outpatient service on smoking cessation was not established. | 100.000.000
| Tobacco use. Specific objective 2.3: Raise awareness of the health risks of tobacco use among the population with a special emphasis on youth and women though educational institutions, workplaces and the media. Reduce tobacco use and exposure to second hand smoking | Organize campaigns on the tobacco use / second hand smoking | Increased number of people correctly identifying the risk of tobacco use | Fully achieved | In the framework of "World No-Tobacco Day", campaigns on the tobacco use / second hand smoking, were organized. Various national studies were conducted to measure the prevalence of smoking in Albania. (ADHS, ESPAD, HBSC, GPS). From 2008 to 2018, the prevalence of smoking is much lower in women aged 15-49 (4% and 5% respectively) compared to the prevalence in men of the same age group (43% and 36% respectively), noticing a steady trend in women and a downward trend in men. (ADHS 2008-09 andA ADHS 2017-18). There is a declining trend of smoking among young people for both women and men aged 15-19 in the two most recent ADHS studies 2008-09 and 2017-18, from 1.1% to 0.9% among women and from 13.4% to 12.3% for men. Prevalence of lifetime smoking among young people (11, 13 and 15 years old) has remained almost identical (12.8% in 2014 and 13.2% in 2018). Smoking prevalence in the past month has slightly decreased in young boys (from 6.8% in 2014 to 6.7% in 2018), but has increased a bit among young girls (from 2.2% in 2014 to 2.7% in 2018). | 5.000.000
| Harmful use of Alcohol. Specific objective 2.4: Review and strengthen the enforcement of the current legislation with special emphasis on: enforcing legislation on restricting access of minors to retail alcohol; enforcing the legislation on banning drink-driving; revise the taxation policy on alcohol products; update the regulatory framework to regulate alcohol content and volume | Strengthen the Health Inspectorate infrastructure and human resource capacities. Establish and maintain the electronic health inspectorate platform | Health inspectorate capacity in enforcing the current alcohol legislation is strengthened | Fully achieved | Law "On protection of minors from alcohol use" No. 9518 date 18.4.2066 was changed into Law 74/2018. This legislation is restricting access of minors to retail alcohol and State Health Inspectorate is enforcing the current alcohol legislation. | Cost is included in the Specific objective 2.1
|  | Monitor the implementation on banning driving under the effect of alcohol use | Excise tax is increased with a consequent increase in the retail price of alcohol products. | Fully achieved | Excise tax is increased with a consequent increase in the retail price of alcohol products.
|  | Organize a workshop on the awareness of the taxation policy on alcohol products with representative for the media, the Chamber of Commerce, the stakeholders etc. Draft recommendations on revising the taxation policy. | Regulatory frameworks on alcohol are updated. | Fully achieved | Alcoholic beverages are subject to excise tax in the Republic of Albania. Regulatory frameworks on alcohol are updated.
| Harmful use of Alcohol. Specific objective 2.5: Raise awareness of the health risks of alcohol consumption among the youth and adult population though the educational institutions, workplaces and the media | Organize campaigns on the health risks of harmful alcohol consumption | Increased number of people correctly identifying the risk of a alcohol use | Fully achieved | Campaigns on the harmful alcohol consumption health risks, were regularly organized. Various national studies were conducted to measure the prevalence of alcohol use in Albania. (ADHS, ESPAD, HBSC, GPS). Also the guidelines and protocols of basic check-up program on individual education about risks of harmful alcohol consumption are available. The check-up manual “Healthy we all are equal!” is available in all health prinamry health centres. The prevalence of alcohol consumption is reduced for both sexes from 63% to 60% for men and from 30% to 28% for women (ADHS 2008-09 and ADHS 2017-18 respectively). There is a decrease in the prevalence of lifetime drunkenness in the HBSC 2017-18 compared with HBSC 2013-14. Hence, in 2014, 13.6% of young people (11, 13 and 15 years old) reported a lifetime episode of drunkenness compared with 9.8% of those in 2018; 4.7% reported 2-3 episodes of drunkenness in 2014 vs. 3.4% in 2018; 1.2% reported drunkenness >10 times in 2014 vs. 1% in 2018. | 5.000.000
| Harmful use of Alcohol. Specific objective 2.6: Increase counseling on harmful alcohol use at the primary health care level through the national check-up program | Draft protocols/guidelines on counseling on the harmful alcohol use | Protocols/guideline are developed | Fully achieved | The guidelines and protocols of basic check-up program on public education about risks of harmful alcohol use are available. The Strategy for Prevention and Reduction of Alcohol Related Harm in Albania 2017-2021 emphasizes the role of public education about risks of harmful alcohol use. | 50
|  | Training of the health staff at primary health care service on the harmful alcohol use | Number of training activities on alcohol use | Fully achieved | Training of the health staff at primary health care service on the harmful alcohol use in the framework of Check-up program, acomplished. In 2018, four trainings were carried out in 2 districts of Albania (Korce and Elbasan) with regard to "Informing and awareness raising of health personnel for importance and usefulness of basic medical check-up among people 35-70 years". During 2016-2020, with regard to harmful alcohol use, 10 trainings in primary health care centers of 5 districts were carried out. During the implementation of the check-up program, 270 training were carried out in 12 regions of the country. | 10.000.000
| Harmful use of Alcohol. Specific objective 2.7: Expand the capacity of alcohol addiction treatment | Expand the capacities on human resources (2 physicians, 2 social workers, 2 psychologists) | Human resource capacity is expanded | Partially achieved | This service operates within Mother Theresa University Hospital. This service has 2 doctors, 7 nurses, 2 genitorial staff, but there are no sociologists and psychologists dedicated for the service of alcohol addiction. There are only 2 psychologists of the general toxicology department that contribute to alcohol adiction service. Doctors themselves provide psychotherapeutic behavioral techniques and clinical rehabilitation for patients. | 40.000.000
|  | Train the human resources in the current centers | Number of training activities | Fully achieved | The health staff is trained on alcohol addiction treatment, accredited by the National Center for Countinous Education. Every month the staff conducts refresher trainings on treatment and rehabilitation protocols based on the permanent access to the European School of Alcohology and Ecological Psychiatry.
|  | Build two new centers ( in the north and south of Albania) | Two centers on alcohol addiction treatment are established | Not achieved | Two new centers on alcohol addiction treatment were not established. | Cost is included on the upcoming Strategy of Prevention of Damage from Alcohol Use
| Harmful use of Alcohol. Specific objective 2.8: Strengthen the capacities of health professionals in identifying the risk of alcohol-related domestic violence and taking appropriate actions | Update the protocols/guidelines on identifying the risk of alcohol-related domestic violence and taking appropriate actions | Protocols/guidelines on identifying the risk of alcohol related domestic violence and taking appropriate actions are developed | Fully achieved | The Strategy for Prevention and Reduction of Alcohol Related Harm in Albania 2017-2021 identifies the risk of alcohol related domestic violence. SOP on domestic violence were developed in 2020. | Cost is included on the upcoming Strategy of Prevention of Damage from Alcohol Use
|  | Train the health staff at primary health care services in identifying the risk of alcohol-related domestic violence and taking appropriate actions | Number of training activities Number of health staff at PHC level trained in identifying the risk of alcohol-related domestic violence and taking appropriate actions | Fully achieved | Family physicians inform, council and educate the population on harmful use of alcohol and alcohol related domestic violence, based on the Primary Health Care Package Services. The check-up manual “Healthy we all are equal!” is available in all health prinamry health centres. In 2018, four trainings were carried out in 2 districts of Albania (Korce and Elbasan) with regard to "Informing and awareness raising of health personnel for importance and usefulness of basic medical check-up among people 35-70 years". During 2016-2020, with regard to alcohol-related domestic violence, 1 training in primary health care centers of 1 districts were carried out. During the implementation of the check-up program, 270 training were carried out in 12 regions of the country. | Cost is included on the upcoming Strategy of Prevention of Damage from Alcohol Use
| Harmful use of Alcohol. Specific objective 2.9: Improve the public transport system to areas close to bars and restaurants to reduce drink driving | Organize a round table on “Improvement of the public transport system to areas close to bars and restaurants to reduce drink driving “ with the main stakeholders (local government MTI, MoH). Monitor the implementations of the round table. | Recommendations from the round table are implemented. | Not achieved | This objective was not achieved. | 100
| Nutrition and physical activity. Specific objective 2.10: Develop national guidelines on physical activities | Develop national guidelines on physical activities | National guidelines on physical activities are developed | Not achieved | National guidelines on physical activities were not developed. Guideline of Check-up program includes education on physical activity for individuals aged 35-70 years old . School curricula were updated to include more hours with physical activity per week. | 100000
| Specific objective 2.11: Promote and sustain the ‘open schools initiative’ to facilitate the physical activity at the community level | Determine the human resources dedicated to the “Open Schools” initiative. | Number of schools under the “Open Schools” initiative | Partially achieved | Training provided by the IPH of health promotion staff in the districts (who play the role of health personnel in schools) on the healthy nutrition of school-age children, according to the package with 12 modules supported by WHO. No activity has taken place since 2016. There are 36 health promotion staff in the 36 districts of Albania who play the role of health personnel in schools, and they regularly work with children and school staff with regard to promotion of physical activity, but mainly focused in schools of urban areas. | No added cost
| Nutrition and physical activity. Specific objective 2.12: Enable the implementation of the training protocols related to physical activity and diet for school health personnel and use of the nutrition modules with special emphasis on rural and remote | Train the school health personnel on physical activity and diet modules (with special emphasis on rural and remote areas) | Number of training activities for the school health staff on the physical activity and diet modules | Partially achieved | Training of school staff with regard to physical activity, was carried out. Also training of children with regard to diet and healthy nutrition was carried out ins some districts of Albania. Pilot study in one school of Tirana for healthy nutrition, was carried out with support of FAO. Round tables with different stakeholders with regard to improve children's health focusing on physical activity and healthy nutrition, were carried out. Food norms for nurseries and kindergartens for the public system were developed by order of the Minister of Health and Social Welfare No. 76/1 date 24/01.2018. But, trainings of the school health personnel on physical activity and diet modules (with special emphasis on rural and remote areas) was not carried out. Training provided by the IPH of health promotion staff in the districts (who play the role of health personnel in schools) on the healthy nutrition of school-age children, according to the package with 12 modules supported by WHO. No activity has taken place since 2016. | 300000
| Nutrition and physical activity. Specific objective 2.13: Work with municipalities to create the conditions for improved physical activity (green spaces, bike lanes, hiking paths) | Advocate to include one major municipality (Tirana) on WHO ‘Healthy City “ project. | Municipality of Tirana is part of on WHO ‘Healthy City “ project ) | Partially achieved | Interventions were as follows: reallocation of road spaces for buses and cyclists, implementation of a bicycle rental system, improving access to public transport for rural neighborhoods and suburbs that do not currently serve as roads, rehabilitation of existing parks, planting trees. But there was no institutionalized collaboration between Tirana municipality and IPH and IC with regard to NCDs action plan implementation. | No added cost
| Nutrition and physical activity. Specific objective 2.14: Build on the existing salt iodization monitoring system to estimate the consumption of salt at the population level | Conduct the survey on consumption of salt at the population level. Prepare and build the capacity for the population-based survey on salt consumption. | Report on the on consumption of salt at the population level | Partially achieved | Report on salt consumption reduction was produced in 2020. This report has a dedicated section on salt consumption based on ADHS 2017-18 data, imports of salt and opinions of citizens. The revision of the Iodized Salt Law was carried out in 2020. | No added cost
| Nutrition and physical activity. Specific objective 2.15: Work with the industry to reduce the salt content in bread maintaining the use of iodized salt based on the standard set by USI law | Conduct a feasibility study on reducing the salt content in bread maintaining the use of iodized salt based on the standard set by the law on “Prevention of the disorder caused by the iodine deficiency in human body “ | Report of the feasibility study on reducing the salt content in bread maintaining the use of iodized salt based on the standard set by the law on “Prevention of the disorder caused by the iodine deficiency in the human body “ | Not achieved | This objective was not achieved. | No added cost
| Nutrition and physical activity. Specific objective 2.16: Increase awareness of healthy nutrition and physical activity among the population | Organize a campaign on healthy eating habits and physical activity | Increased number of people that reported healthy eating habits and physical activity. | Partially achieved | Campaigns on healthy eating habits and physical activity were carried out only in international specific days (in the framework of health promotion calendar). Organized a campaigns on healthy eating habits weren't carried out. Family doctors promote healthy eating to individuals aged 35-70 years based on check-up program guidelines. The prevalence of overweight and obesity in Albania has been estimated in two studies ADHS 2008-09 and ADHS 2017-18 and the comparison of indicators has been done for children under 5 years, for young people and adults. The prevalence of overweight in children under 5 has decreased from 2008 to 2018, for both sexes. From 2008 to 2018, the prevalence of overweight has decreased in both young people and adults, while the prevalence of obesity is increasing for both youth and adults of both sexes. In the latest ADHS 2017-18 study, the physical activity and the daily consumption of fruits and vegetables for the population was estimated. Only about 5% of women and 2% of men age 15-49 consumed the daily recommended combined number of portions of fruits and vegetables. Overall, about 1 in 10 women and men age 15-49 engage in frequent physical activity. According to HBSC 2017-18 study, one in four young people in Albania conducts physical activity on a daily basis. One in two young people consume fruit more than once per day and one in three young people consume vegetables more than once per day. In HBSC 2017-18 there is evidence of an increase in the frequency of physical activity (3- 7 days) compared with the HBSC 2013-14. Thus in 2018, 77.4% of young people reported to conduct physical activity 3-7 days per week compared with 74.2% of young people in 2014. From 2014 to 2018 there is an improvement of daily consumption of fruit and vegetables among young people. In 2018, 63.3% of young people reported to consume fruit every day compared with 50% of those in 2014. Also in 2018, 48.7% of young people consumed vegetables daily, compared with 37.2% of young people in 2014. | 500000
|  | Implement the “check- up “ |  | Fully achieved | Assessment, counseling, treatment and follow-up for lifestyle factors were carried out by the family physician. | No added cost
| Nutrition and physical activity. Specific objective 2.17: Review and update the national nutrition guidelines | Review and update the existing guidelines and protocols on nutrition with specific focus on adults and adolescents. | Update of the guidelines and protocols on nutrition with specific focus on adults and adolescents. | Not achieved | The national nutrition guidelines were not developed. Check-up program guidelines on healthy eating and nutrition are available for 35-70 years old age groups. The nutrition norms for Gard of the Republic were updated in 2020. | 300.000
| Nutrition and physical activity. Specific objective 2.18: Promote breastfeeding | Strengthen of the implementation of the law on “Promotion and protection of breastfeeding “ | Number of the monitoring acts on implementation of the law on “Promotion and protection of breastfeeding “ | Fully achieved | Law "On promotion and protection of breastfeeding" updated in 2019. The health information system is collecting data on core and standardized indicators on: early initiation of breastfeeding, exclusive breastfeeding, continuation of breastfeeding, introduction of complementary feeding) and growth monitoring (weight for age, height for age and weight for height). This system scaled-up at national level in 2016 following a series of training and supportive supervision activities covering key health professionals from all regions of Albania. During 2017, the paper based system was transformed into mainly a web based system functioning as a national web based system for data collection, analysis and reporting (at the level of the regional departments of health), and paper based at the service delivery point (at the level of health centers). | No added cost
|  | Evaluation of hospitals bearing the ”Baby-Friendly Hospital” certificate | Report on the evaluation of hospitals of hospitals bearing the ”Baby-Friendly Hospital” certificate | Not achieved | The implementation of the Friendly Child Initiative has been an integral part of the UNICEF and MoH Breastfeeding Program since 1996. The implementing partner of the Friendly Child Hospital Initiative has been since 1998 the Albanian Group for the Protection and Promotion of Breastfeeding , member of IBFAN, and since 2004 onwards Center for Healthy Childhood. Year 1996: Started the implementation of the Child Friendly Hospital Initiative under the Breastfeeding Program, UNICEF & MoH. Year 2000: The process of certification of maternity hospitals for the title of Child Friendly was established. The National Team of External Evaluators for the Child Friendly Hospital Initiative was also established in 2000. Year 2002: The National Trainers Team was established (TOT: WHO & UNICEF 40-hour course "Breastfeeding Counseling"). During the period 2016-2020 there were no activities related to the Child Friendly Hospital Initiative. | 100000
|  | Expand the initiative of the ”Baby Friendly Hospital” | Increase the number of ”Baby-Friendly Hospital” | Not achieved | The number of Child Friendly hospitals has not increased because the Initiative has stopped after 2013.
|  | Establish a model on creating a “mothers with baby“ group for promoting the breastfeeding | The model on “mother and baby“ group promoting breastfeeding is established. | Partially achieved | The initial model for the establishment and functioning of such groups was first established in Fier in 2004, then in Kukes, Puke, Tropoja and Durres (Shijak and Xhafzotaj) in 2012-2013. 9 maternity hospitals in the 9 main districts of the country have established the Protocol for breastfeeding based on the Mother and Baby model. In 2013, this initiative was extended to primary health care centers in the district of Durres. In 2014, as part of the Clinical Practice Protocols (PPK), including "10 Steps for Successful Breastfeeding in the community" was approved. During the period 2016-2020 there were no activities related to this initiative. | 3.000.000
| Nutrition and physical activity. Specific objective 2.19: Build on the existing primary care training programs related to the physical activity and nutrition; ensure continuous training of all relevant staff | Train the health staff at primary health care services on physical activity and nutrition | Number of training activities for the health staff at primary health care services on physical activity and nutrition | Fully achieved | Trainings of the health staff at primary health care services on physical activity and nutrition were carried out during the implemenatation of basic health check-up program. The check-up manual “Healthy we all are equal!” is available in all health prinamry health centres. In 2018, four trainings were carried out in 2 districts of Albania (Korce and Elbasan) with regard to "Informing and awareness raising of health personnel for importance and usefulness of basic medical check-up among people 35-70 years". During 2016-2020, with regard to physical activity and nutrition, 23 trainings in primary health care centers of 6 districts were carried out. During the implementation of the check-up program, 270 training were carried out in 12 regions of the country. | Cost is included in activity of speciifc objective 2.2
| Nutrition and physical activity. Specific objective 2.20: Review the existing regulation-initiatives related to reducing the marketing pressure of food and non-alcoholic beverage to children and propose specific recommendations | Desk review of the existing regulation-initiatives related to reducing marketing pressure of food and nonalcoholic beverage to children and propose specific recommendations | Report on review the existing regulation-initiatives related to reducing marketing pressure of food and non-alcoholic beverage to children | Partially achieved | Law "On protection of minors from alcohol use" No. 9518 date 18.4.2066 was changed into Law 74/2018. This law, along with alcoholic beverages, introduces energy drinks and carbonated drinks that contain added sugar. The provision of alcoholic and energy drinks to minors is prohibited. There were no revised regulations related to reduce marketing pressure of food to children. | 100000
|  | Organize round tables to present the review findings and articulate recommendations for the decision makers | Present the findings and recommendations at round tables | Partially achieved | Round tables with regard to revise the regulations related to reducing marketing pressure of nonalcoholic beverage (but not of food) to children, were organized. | 250000
| Nutrition and physical activity. Specific objective 2.21: Assess the current amount of trans-fats in the food chain and estimate the cost-benefit of potential measures to reduce trans-fats | Assess the current amount of trans-fats in the food chain. | Report on the assessment of the current amount of trans-fats in the food chain | Not achieved | The current amount of trans-fats in the food chain was not assessed. | 100000
|  | Estimate the cost-benefit of potential measures to reduce trans-fat | Report on the cost-benefits of potential measures to reduce the trans-fat content. | Not achieved | The cost-benefit of potential measures to reduce trans-fat was not estimated. | 100000
|  | Establish the laboratory capacity on the trans-fat content assessment in the chain food at IPH | The lab capacity on the trans-fat assessment in the chain food at IPH is established. | Not achieved | The laboratory capacity on the trans-fat content assessment in the chain food at IPH was not established. | N/A
Domain 3: Health Systems. STRATEGIC OBJECTIVE 3: Strengthen integration, accountability and rational use of services for improved management of NCDs | Specific objective 3.1: Assess the health system in relation to NCD prevention and control | Conduct a health system assessment in relation to NCD prevention and control | Report on the health system assessment with the follow-up priority actions | Fully achieved | A health system assessment in relation to NCD prevention and control was conducted and "Primary Health Care in Albania, a Comprehensive Assessement" report, was produced in 2018. This assessement was conducted based on WHO standards. | 50000
| Specific objective 3.2: Develop and update the clinical, NCD-related, evidence based guidelines at all healthcare levels and ensure their effective implementation | Update the clinical guideline at the primary, secondary and tertiary levels. | Clinical guidelines at the primary, secondary and tertiary level are produced | Fully achieved | Clinical guidelines for prevention, diagnosis and control of several chronic diseases (for cardiovascular diseases, diabetes, hypertension, cancer, chronic pulmonary disease including asthma, mental conditions, elderly people, etc.), were updated in 2019. Also there are guidelines for case follow-up based on the findings of the basic medical check-up for citizens aged 35-70 years old. | 500000
| Specific objective 3.3: Extend the set of indicators and feasibility of systems to better monitor the quality of care for diabetes complications, asthma-related deaths, myocardia fatality rate | Extend the set of indicators on quality of care | The set of indicators monitoring the quality of care is established. | Partially achieved | There are quality standards for accreditation of primary health care institutions, approved by the National Center for Quality Assurance and Accreditation of Health Institutions. Also, there are hospital performance indicators approved by the National Center for Quality Assurance and Accreditation of Health Institutions. | 50000
|  | Draft the data collection manual. Develop administrative orders to measure the performance through the quality of care indicators. | Report on the quality of care is produced | Partially achieved | Annual report with regard to some indicators on quality of care is produced by the Compulsory Care Health Insurance Fund. The purpose of this report is to inform the public on the management of the compulsory health care insurance scheme, in accordance with the national health care policies presented throughout the annual activity of the institution. | No added cost
| Specific objective 3.4: Ensure the quality of early detection/ screening approaches and integrate with all levels of the health system, e.g. breast, colorectal and cervical cancers; PHC check-ups; occupational health hazards | Prepare the pathways to follow up the identified cases | Pathways on following up of the positive identified cases are established | Fully achieved | Pathways on following up of the positive identified cases through check-up program, cervical cancer screening, breast cancer screening and colorectal cancer screening were established. | 50000
|  | Decentralize the chemotherapy center for better access to cancer treatment | The number of centers providing chemotherapy is increased | Fully achieved | Except of Tirana, the number of centers providing chemotherapy is extended to other main districts of the country such as Durres, Korça, Fier, Shkoder and Vlore. | No added cost
|  | Prepare a report on the access to and rationale use of technologies on screening, diagnosis of, treatment of, control over, rehabilitation from and palliative care for NCDs | A report on access to and rationale use of technologies on screenings diagnosis of, treatment of, control over, rehabilitation from and palliative care for NCD is developed. | Partially achieved | A report on access to and rationale use of technologies on screenings regarding cervical cancer and breast cancer screening is developed. But no report was prepared with regard to treatment of, control over, rehabilitation from and palliative care for NCDs. | 300000
|  | A pilot population-based cervical cancer screening for future expansion | Findings and recommendations from the pilot population-based cervical cancer screening are implemented | Fully achieved | Findings and recommendations from the pilot population-based cervical cancer screening were implemented and therefore the National Cervical Cancer Screening Program was established in 2019. | N/A
| Specific objective 3.5: Enhance the coverage of the cardio-metabolic risk assessment tool and expand the coverage for the 40 to 65 year old population | Monitor the use of cardio-metabolic risk assessment tool | Report on the monitoring of the cardio-metabolic risk assessment tool. | Fully achieved | There is a cardio-metabolic risk assessment tool in the framework of Check-up program and the report of the main findings of the check-up program was produced. | 50000
|  | Train the health staff on the use/interpretation of cardio-metabolic risk assessment tool | Number of training activities on the use/interpretation of cardiometabolic risk assessment tool. | Fully achieved | During the implementation of the basic check-up program, all the relevant health staff were trained with regard to use and interpret the cardio-metabolic risk assessment tool. Cardiovascular risk stratification is done applying SCORE methodology for population 35-70 years old through preventive check-up programme. During 2016-2020, with regard to cardiometabolic risk assessment tool, 16 trainings in primary health care centers of 9 districts were carried out. During the implementation of the check-up program, 270 training were carried out in 12 regions of the country. | Cost is included in the activity of specific objectve 2.2
|  | Present the findings in the national public health conference |  | Fully achieved | Findings of the basic check-up program report were presented at the Scientific Forum organized in 2019.
| Specific objective 3.6: Effective management of acute cardiovascular events | Implement the new emergency care model | Emergency care system is functional | Fully achieved | The National Emergency Medical Center was established in 2014, is functional and the emergency medical services are provided at all the levels of health care (primary, secondary and tertiary). National Emergency Medical Center has been empowered after 2017. | 100.000.000
|  | Train the emergency care staff on the effective management of acute cardiovascular events | Number of training activities on the effective management of acute cardiovascular events | Fully achieved | The staff is counstinuously trained according to the activities of the National Continuing Education Center. During 2016-2020, with regard to effective management of acute cardiovascular events, 18 trainings in 12 regions were carried out.
|  | Establish the network of the medical emergency center during summer. | Emergency centers are functional during summer in the touristic destinations | Fully achieved | Emergency centers are functional during summer in all the touristic destinations of Albania, by an annual order of Ministry of Health and Social Welfare.
| Specific objective 3.7: Ensure equitable access to NCD-related drugs | Improve management, planning and procurement of NCD-related drugs | Procurement procedure on NCD-related drugs is improved. | Partially achieved | Each year, primary health care centers proccure a list of emergency medicines (including NCD related drugs). New Primary Health Care Strategy 2020-2025 empowers health centers by making them more independent to buy their own medicines. | No added cost
|  | Improve the access to the essential drug list | Better the access to the essential drug list related to NCD treatment. | Fully achieved | Almost every year, the essential drug list related to NCD treatment is expanded.
|  | Put in place the drug track and trace system in all hospitals | Drug track and trace is system is established | Fully achieved | Drug track and trace is system is established. There is an electronic system for e-referral, e-prescription, e-farmacy, e-drugs, e-registry, e-complaint, e-albania (to find the family physician).
| Specific objective 3.8: Ensure that the uninsured population receives free services in the primary health care services 2016 -2020 | Lift the financial barriers to visits in the PHC level | Health visits to the primary health care level are free of charge | Fully achieved | Health visits to the primary health care level are free of charge based on the basic service package in primary health care (Decision of the Council of Ministers No. 308 date 21.05.2014, revised and updated in 2018). Another Decision of the Council of Ministers No. 955 date 29.12.2014 (revised in 2018) defines the categories that will be excluded from direct payments for health services, which are part of the list of reimbursable medicines of packages of primary health care services and hospital care covered by the compulsory health insurance scheme. This decision states the exemption from direct payments for the first alternative drugs on the list of reimbursable medicines for persons with chronic diseases, according to the list approved by order of the Minister of Health. The categories that profit are as follows: children 0-18, disabled persons, veterans, ex-convicts and political persecuted persons, orphans, persons receiving disability benefits, retirees, detainees and prisoners, asylum seekers, victims of trafficking. | No added cost
|  | Minimize the financial barrier on the other levels of health care in respect of the referral system | Health visits at the other levels of health care in respect of the referral system have less financial burden for the uninsured patients | Fully achieved | Health visits at the other levels of health care in respect of the referral system have less financial burden for the uninsured patients based on Decision of the Council of Ministers No. 308 date 21.05.2014, revised and updated in 2018 and Decision No. 955 date 29.12.2014 revised in 2018.
|  | Provide the free of charge check-up package for the 35-70 year old population at the primary health care level | The check-up package for the 35-70 year old population at the primary health care level is free of charge | Fully achieved | The check-up package for the 35-70 year old population at the primary health care level is free of charge.
| Specific objective 3.9: Develop, improve and reorient the continuing educational training programs in the field of NCD prevention and control | Introduce the instruments to promote continuing education for nurses and physicians at the primary care level in the field of NCDs | Instruments to promote the continuing education for nurses and physicians are developed. | Fully achieved | With regard to check-up program, all the relevant health staff is trained at the primary health care level in the field of NCDs. The staff is counstinuously trained according to the activities of the National Continuing Education Center. There is in place a recertification system (by state exam) for doctors and nurses in case they do not meet the required credits. | No added cost
| Specific objective 3.10: Strengthen the patient education programs for diabetic patients (and scale up for other NCD conditions) | Establish the cabinets for education of the diabetic patients at the district level. | Number of education cabinets for diabetic patients at district level. | Partially achieved | With regard to diabetes education, according to "Primary Health Care in Albania, a Comprehensive Assessement, WHO 2018" report, the coverage with education cabinets for diabetic patients was reported around 70 percent. | 20.000.000
|  | Create a model for the education of patients with IAM or AVC | A model on education of patient with IAM/ACV is established | Partially achieved | With regard to IAM/ACV education of patients, according to "Primary Health Care in Albania, a Comprehensive Assessement, WHO 2018" report, all urban and suburban health centres report a high proportion of educated patients (>70%) which undergoes cardiovascular disease risk assessment (SCORE methodology) based on check-up programme. Patient education at the primary health care center evolve along with assessing the risk of cardiovascular disease.
| Specific objective 3.11: Develop a human resource plan to address mal-distribution and shortage of professionals related to NCD management and surveillance at both public health and clinical settings | Enable the balanced distribution of health professionals related to NCDs | Human resource plan is developed | Partially achieved | The government has acknowledged the shortage of specialists and since February 2019 is addressing it through: patronage and bonus systems and binding contracts for new specialists to work in districts outside the capital, Tirana, for free training. | No added cost
|  | Introduce incentives in order to cover areas underserved with NCD services | Incentives in order to cover areas underserved with NCD services are proposed and implemented. | Fully achieved | The government has acknowledged the shortage of specialists and is addressing it through: patronage and bonus systems; binding contracts for new specialists to work in districts outside the capital, for free training (from February 2019); allowing those not on a government contract to apply to work in districts for bonus payments. This is supported by the guidance of the Minister of Health and Social Welfare no. 499 date 02/07/2019.
| Specific objective 3.12: Expand the integration of the public and private sectors through a single purchasing system to maximize the potential of human resource to address NCDs | Implement the check-up package for the 35-70 years old population at the primary health care level. | Percentage of the 35-70 year old population receiving the check-up package for the 40-65 years old population at the primary health care level | Fully achieved | The check-up package for the 35-70 years old population at the primary health care level is fully implemented. In 2018, four trainings were carried out in 2 districts of Albania (Korce and Elbasan) with regard to "Informing and awareness raising of health personnel for importance and usefulness of basic medical check-up among people 35-70 years". As of February 2018, 954,667 visits have been made under the program. The majority of participants were female with 61% of the total visits. 27.5% of visits were carried out during the first year of the program, while 36.9% and 35.5% were carried out during 2016 and 2017, respectively. Up until February 2018, 54% of all 954 667 check-up visits were carried out in rural areas. Overall, the check-up programme raised the awareness of the population for the need of preventive check-ups, with 60% of the people eligible for the check-ups attending at least once in the period March 2015–March 2018. | No added cost
|  | Enable the cardiovascular interventions package (coronary angioplasty and angiography; definitive pacemaker; aortocoronary bypass, valvuloplasty) to be applied in private hospitals covered by the CHCIF | The cardiovascular interventions package (coronary angioplasty and angiography; definitive pacemaker; aortocoronary bypass, valvuloplasty) is provided in the private hospital and funded by the CHCIF. | Fully achieved | Ministry of Health and Social Welfare and CHCIF through the initiative "Health service packages, new patient-focused funding", concluded contracts with private hospitals for the provision of health packages to be funded by the CHCIF, mainly in the field of nephrology and cardio-surgery.
| Specific objective 3.13: Expand the NCD-related palliative care services | Establish the palliative care center close to the regional hospitals. | The palliative care service is expanded. | Partially achieved | There is one public palliative care service in Tirana "Oncology Service at Home" and two private palliative care services Rider (operates in Tirana and Durres) and Mary Potter (operates in Korce). This service is provided free of charge to the patients. The regional hospitals of Shkodra, Vlora, Fieri, Korça and Elbasan, that have an oncologist doctor, they provide palliative care services with a total of 1-2 dedicated beds. There is a law "On palliative care" No.138/2014 and Decision of Council of Ministers No. 101 date 4/2/2015 and the Primary Health Care Package updated in 2019, that specify the role of primary health care centres including the provision of palliative care. Family physicians offer basic palliative care services such as: they prescribe the reimbursable drugs for cancer patients and provide at home services like morphine injection etc. | Included on the Strategy of Palliative Care
|  | Expand the drug reimbursement list on palliative care. | The palliative drugs are included in the drug reimbursement list. | Partially achieved | Some of the medicines used in palliative care are included in the drug reimbursement list.
|  | Training of the health staff at primary health care level on palliative care (with the focus on underserved areas) | Number of training activities on palliative care/Number of health staff at primary health care (focus on underserved areas) trained on palliative care | Partially achieved | Few trainings of the health staff at primary health care level with regard to palliative care (with the focus on underserved), were carried out. During 2016-2020, with regard to palliative care, 53 trainings in primary health care centers of 11 districts were carried out.
Domain 4: Surveillance-Research (HIA). Specific Objective 4:Establish a comprehensive and coordinated national surveillance system | Specific objective 4.1: Upgrade the existing death registration system by introducing ICD-10 | Translate and adopt ICD 10 | ICD 10 is introduced and adopted | Partially achieved | ICD 10 is translated in Albanian, and technical meetings for the introduction of ICD10 were held. Only in Tirana, the capitol city, a pilot training was carried out (trainer of trainers). | No added cost
|  | Establish a coordination mechanism for the management of updates and adaption of health information system | The coordination mechanism for the management of updates and adaption of health information is established | Not achieved | The coordination mechanism for the management of updates and adaption of health information was not established. | No added cost
|  | Train the staff dealing with the ICD 10 | Number of staff trained on ICD 10 | Partially achieved | A pilot training was carried out only for trainer of trainers. 15 persons were trained. | 2.000.000
| Specific objective 4.2: Establish a national population-based cancer registry | Implementation of the Decree of the Council of Ministers and the ministerial order | National population-based cancer registry is established | Fully achieved | National population-based cancer registry is established since 2015 and is functioning very well, based on the Council Decision of Ministers of 2014. | Included on NCCAP
| Specific objective 4.3: Establish a national hospital-based IAM and stroke registry | Implement the Decree of the Council of Ministers. | National hospital-based registry IAM and Stroke is established | Fully achieved | Based on the Decision of Council of Ministers of 2014, IAM and Stroke national hospital-based registries were established in 2015 and are functioning very well. | No added cost
|  | Develop the data collection manual. | Data collection manual is developed | Fully achieved | Data collection manual is developed and all the relevant staff is trained in data collection and reporting. | No added cost
|  | Train the health staff at district/regional hospital and public health directorates responsible for the data collection | First report at national level is published | Fully achieved | First report on NCDs at national level was published in 2018. The report included information on incidence, prevalence and mortality data for the main NCDs in the country. The health staff at district/regional hospital and public health directorates responsible for the data collection were trained. | 1.000.000
| Specific objective 4.4: Make better use of the existing quality of care and health care utilization data focusing on the distribution and quality of care monitoring | Develop reports on health care utilization and quality of care at national/regional levels | Reports on the quality of care and health care utilization are published | Partially achieved | Some indicators on the quality of care and health care utilization are produced by the Compulsory Health Care Insurance Fund, Ministry of Health and Social Welfare and Health Care Services Operator. "Primary Health Care Assessement in 2018", carried out by WHO provides data on the quality of care and health care utilization. The Strategy of Health Care Services Operator recommends yearly assessemnet of the quality of care and health care utilization. In 2019, National Center for Quality, Safety and Accreditation of Health Institutions has introduced the quality monitoring of health care services. | 500000
|  | Build on the new system of check-up to produce quality of care indicators | Reports on the quality of care and health care utilization are published | Partially achieved | The check-up system produces some quality of care indicators. | 500000
| Specific objective 4.5: Make the global NCD framework in Albania operational | Standardize the DHS to align with the Global NCD Monitoring Framework and its indicators | Global NCD framework is included in the national survey | Fully achieved | ADHS 2017-2018 provides information on the prevalence of NCDs and lifestyle health risk factors and the global NCD framework was included in the national survey. | No added cost
|  | Prepare and plan for the development of periodic national comprehensive risk factor surveys based on WHO STEPS. | Epidemiologic report on risk factor based WHO STEPS | Partially achieved | ADHS 2017-2018 provides information on the prevalence of NCDs and lifestyle health risk factors and the global NCD framework was included in the national survey. But this report was not fully based on WHO STEPS.
|  | Continue and coordinate specialized risk factor surveys based on school settings, e.g. HBSC, COSI, GYTS, ESPAD, YRBS | Epidemiologic report on risk factor based HBSC, COSI, GYTS, ESPAD, YRBS | Partially achieved | HBSC report on risk factor based was conducted in 2018, meanwhile ESPAD was conducted only in 2011 and 2015 and COSI was conducted in 2013 and 2016; GYTS was last conducted in 2020 and YRBS was last conducted in 2018. The third round of ESPAD and COSY were not carried out.
| Specific objective 4.6: Scale up the under-5 child nutrition surveillance nation wide | Develop a data collection manual | Nutrition surveillance is established. | Fully achieved | The nation wide under-5 child nutrition surveillance was established since 2017 and functions very well. | No added cost
|  | Train the health staff on data collection and reporting | First report on the surveillance of nutrition of under five children is produced | Fully achieved | Annual report of under-5 child nutrition surveillance is produced.
| Specific objective 4.7 Institutionalize the integration of an NCD surveillance framework as part of the national health information system | Develop and ensure the linkage between the -e prescription / -e health records / -“check-up “-e health card / aiming at the NCD surveillance | NCD surveillance is integrated in the health information system | Fully achieved | NCD surveillance is integrated in the health information system. There is an electronic platform for e-referral, e-prescription, e-farmacy, e-drugs, e-registry, e-complaint, e-health, e-albania (to find the family physician). | No added cost
| Specific objective 4.8: Improve the quality and scope of NCD and risk factor surveillance system to include information about the socioeconomic and occupational statuses. | Revise the data collection and analysis methodology | NCD risk factors are analyzed by the basic socioeconomic indicators, e.g. geographic distribution, education, employment status | Fully achieved | NCD risk factors are analyzed by the basic socioeconomic indicators, e.g. geographic distribution, education, employment status. These data are collected through national surveys such as ADHS and through the information gathered from check-up program. | 50000
| Specific objectve 4.9: Assure the disaggregation of service utilization and health outcome data by basic socioeconomic indicators, e.g. geographic distribution, education, employment status | Revise the data collection and analysis methodology | Service utilization and health outcomes are analyzed by basic socioeconomic indicators, e.g. geographic distribution, education, employment status | Partially achieved | Health outcomes are analyzed by basic socioeconomic indicators, e.g. geographic distribution, education, employment status. But the dissagregation is not yet possible for service utilization data. | Cost is included in the activity of specific objective 4.8
| Specific objective 4.10: Develop the capacity for the health impact assessments and doing further research in this area | Exchange program with European Center on the health impact assessment. | Number of people attending the exchange programs on the health impact assessment. | Partially achieved | Few specialists from Institute of Public Health and Ministry of Health and Social Welfare attended short international workshops, but were not part of exchange programs with European Center. | 600000
| Specific objective 4.11: Evaluate the implementation of the implementation plan based on the monitoring of the evaluation framework. | Produce a midterm/final report on the implementation of the NCD program | Report prepared | Fully achieved | Biannual reports prepared based on WHO matrix were produced. NCDs report was produced in 2018 by Institute of Public Health. The present evaluation report of Action Plan on Non-Communicable Diseases 2016-2020. | 50000
| Specific objective 4.12: Strengthen the analytic capacity at local and national levels to analyze the available database | Establish an exchange program with European Center | Number of trained professionals on analyzing the available database | Not achieved | The exchange program with European Center was not established. | 600 000
|  | Publish a special edition on the Albanian Medical Journal on NCD topics | Number of publication on NCD topics | Fully achieved | NCDs report was produced in 2018 by Institute of Public Health. A report on achievment of SDG related to health was carried out in collaboration by UMT students and IPH, financed by WHO in 2019.
|  | Make presentations of the research on NCDs in Public Health Conferences. | Number of publication on NCD topics | Fully achieved | Presentations of the research on NCDs in Public Health Conferences were carried out.